NATIONAL COUCIL ON DISABILITY AFFAIRS

ACCOMPLISHMENT REPORT

JANUARY – OCTOBER 2013

OED – REGIONAL PROGRAMS COORDINATOR

| PROGRAMS/ACTIVITIES/PROJECTS | TARGETS | ACCOMPLISHMENTS (Quantity) | DESCRIPTION OF RESULTS (Quality) | REMARKS |
| --- | --- | --- | --- | --- |
| STRATEGIC PRIORITIES – GOAL I: INCREASE THE NUMBER OF LGUs COMPLIANT TO DISABILITY-RELATED POLICIES, LAWS, PROGRAMS AND SERVICES Capacity building activities for cities and municipalities to implements disability related laws and policies Conduct of Regional/Local Consultations on building an inclusive and barrier-free environment | 17 Regions 48 Local Government units | 15 Regions 84 Local Government Units | Fifteen (15) were able to conduct consultation with local stakeholders namely, District Engineers, Local Building Officials, leaders of PWDs and other local stakeholders; The activity resulted to the organization of the following: 68 District Access Monitoring Teams; 5 Provincial Access monitoring Teams; 1 City Access monitoring Teams | Conducted Regional Consultations with District Engineers, Local Building Officials and leaders with disabilities; Region 7 has not conducted the same as of date. The conduct of the activity is set on December 03, 2013; |  |
| PROGRAMS/ACTIVITIES/PROJECTS | TARGETS | ACCOMPLISHMENTS (Quantity) | DESCRIPTION OF RESULTS (Quality) | REMARKS |
|  |  |  | 14 Municipality Access Monitoring Teams. Total: 84 Access Monitoring Teams |  |
| GOAL II: ESTABLISH DATA BASED SYSTEM ON DISABILITY-RELATED INFORMATION – Develop data bases/systems on disability-related information | Collect data from 64 LGUs/NGAs | 151 LGUs 5 Regional Office (DPWH) Total – 156 | Data collected as follows: (LGUs/NGAs) Newly created PDAO – 21 PWD ID Issuance – 105 Employment of PWDs – 25 DPWH Report on Access Audits – 5 Regions |  |
| GOAL III: INCREASE THE NUMBER OF DISABILITY-RELATED STRUCTURES IN THE LGUS FROM 96 TO 150 BY DECEMBER 2013 – Lead in the organization of functional disability-related structures in cities and municipalities Lead in the provision of support services for persons with disabilities and their families/support and advocates | 54 Structures Provide services/support to 40 PWDs | 112 structures Provided services/support to 109 PWDs | Access Monitoring Teams -75 Sub-com – 35 Local Committees – 2 PWDs provide Wheelchairs – 66 Canes – 24 Laptops 15 Referrals - 21 |  |
| PROGRAMS/ACTIVITIES/PROJECTS | TARGETS | ACCOMPLISHMENTS (Quantity) | DESCRIPTION OF RESULTS (Quantity) | REMARKS |
| B. OTHER KRAs/OTHER FUNCTIONS- Lead in the consultation with PWDs/CSOs/NGAs/LGUs in the formulation of the National Disability Strategy and Decade Plan of Action | Conduct 48 consultations | Conducted 62 consultations | Consultations were conducted with various stakeholders especially PWDs and local service providers to gather inputs in the formulation OF ction plans that will form part of the National Decade Plan |  |
| C. DIRECTIVE FROM THE SECRETARY- Capacitate LGUs/DPOs/NGAs to develop advocacy plans | 30 LGUs to be capacitated | 78 LGUs capacitated | LGUs were provided new developments on disability such as the Incheon Strategy, the need to organized access monitoring teams and other disability structures at the local level to enhance compliance of THE laws. |  |